## Sheet1
Team: | [9D -Arnar Pétursson arp25@hi.is Freyr Saputra Daníelsson fsd1@hi.is Leifur Daníel Sigurðarson lsd2@hi.is ] |  |  | Unit: person-days (assuming 2 productive hours per person-day)
Sprint | User Story ID | User Story | Priority | Estimated Team Effort | Actual Team Effort | Done?
1 | 18 | As a website visitor, I would like to be able to book the tours I am interested in, to secure my place in the trip. | 10 | 6 | 2
1 | 19 | As a website visitor, I would like to receive a confirmation email for the trips I have booked, to ensure my booking took place. | 10 | 3 | 1
1 | 2 | As a website visitor it is crucial for me that the website is available in english. | 20 | 2 | 1
2 | 10 | As a website visitor, I would like to see the duration of each tour so I can plan my day efficiently | 30 | 1
2 | 6 | As a tourist, I want to submit a review for a day tour I've been on, to let others know what my experience was and what to expect | 40 | 10
2 | 12 | As a tourist, I would like to be able to search for tours depending on their location, so I can plan my day efficiently. | 50 | 3
2 | 4 | As a travel agent, I would like to filter out day trips available depending on the size of my customer group, to save me time while browsing tours. | 60 | 13
2 | 11 | As a traveler, I would like to see the difficulty level of the tour, to see if it suits me. | 60 | 1
2 | 15 | As a website visitor, I want to be able to see the itinerary for each tour, to know what to expect. | 60 | 1
2 | 16 | As a traveler, I would like to be able to search for trips depending on their price, so I can plan my budget efficiently. | 60 | 1
3 | 17 | As a website visitor, I would like to be able to browse trip categories, so I can find a trip I am interested in. | 70 | 2
3 | 8 | As a website visitor, I want to see what tours are popular, so I don't have to spend time searching for good tours | 80 | 2
3 | 9 | As a website visitor, I want to see photos from day tours, so I know what to expect | 90 | 13
3 | 1 | As a marketing manager, I want to reply to reviews in public or private, in order to address any mentioned concerns. | 100 | 5
3 | 3 | As a customer, I want to endorse reviews that i agree with, to make the review more reliable. | 110 | 2
4 | 20 | As a tourist, I would like to receive a reminder email the day before, so I don´t forget my trip. | 110 | 2
4 | 7 | As a webmaster, I want to be able to verify reviews before they appear on the website, to make sure it isn't spam | 120 | 4
4 | 5 | As a traveler, I would like to see tours that are on special offer, to be able to find something that i might like with better pricing. | 130 | 10
5 | 13 | As a tourist, I want to be able to submit a rating and a review for the guide that was on the tour I've been on, to let others know my experience and what to expect. | 140 | 3
5 | 14 | As a website visitor, I want to be able to see which guide is on each tour, to check his reviews and know what to expect. | 140 | 3
(á eftir að margfalda *2 til að fá klukkutíma (Í Estimated Team Effort))