## Sheet1
Team: | [9D -Arnar Pétursson arp25@hi.is Freyr Saputra Daníelsson fsd1@hi.is Leifur Daníel Sigurðarson lsd2@hi.is ] |  |  | Unit: person-days (assuming 2 productive hours per person-day)
Sprint | User Story ID | User Story | Priority | Estimated Team Effort | Actual Team Effort | Done? | Estim. Team effort [Hours] | Actual [Hours
1 | 18 | As a website visitor, I would like to be able to book the tours I am interested in, to secure my place in the trip. | 10 | 6 | 5 | YES | 3 | 2.5
1 | 19 | As a website visitor, I would like to receive a confirmation that I have booked, to ensure my booking took place. | 10 | 3 | 1 | YES | 1.5 | 0.5
1 | 2 | As a website visitor it is crucial for me that the website is available in english. | 20 | 2 | 1 | YES | 1 | 0.5
2 | 10 | As a website visitor, I would like to see the duration of each tour so I can plan my day efficiently | 30 | 1 | 1 | YES | 0.5 | 0.5
2 | 6 | As a tourist, I want to submit a review for a day tour I've been on, to let others know what my experience was and what to expect | 40 | 10 | 5 | YES | 5 | 2.5
2 | 12 | As a tourist, I would like to be able to search for tours depending on their location, so I can plan my day efficiently. | 50 | 3 | 2 | YES | 1.5 | 1
2 | 4 | As a travel agent, I would like to filter out day trips available depending on the size of my customer group, to save me time while browsing tours. | 60 | 13 |  | NO | 6.5
2 | 11 | As a traveler, I would like to see the difficulty level of the tour, to see if it suits me. | 60 | 1 | 1 | YES | 0.5 | 0.5
2 | 15 | As a website visitor, I want to be able to see the itinerary for each tour, to know what to expect. | 60 | 1 | 1 | YES | 0.5 | 0.5
2 | 16 | As a traveler, I would like to be able to search for trips depending on their price, so I can plan my budget efficiently. | 60 | 1 | 1 | YES | 0.5 | 0.5
3 | 17 | As a website visitor, I would like to be able to browse trip categories, so I can find a trip I am interested in. | 70 | 2 | 1 | YES | 1 | 0.5
3 | 8 | As a tourist, I would like to be able to search for tours that do pickup, so I can plan my day efficiently. | 80 | 2 | 1 | YES | 1 | 0.5
3 | 9 | As a marketing manager, I would like to be able to make a new trip, so it can be viewed on the site | 90 | 5 | 2 | YES | 2.5 | 1
3 | 1 | As a marketing manager, I want to be able to accept all pending reviews, to save time when I know reviews are not spam | 100 | 1 | 1 | YES | 0.5 | 0.5
3 | 3 | As a customer, I want to endorse reviews that i agree with, to make the review more reliable. | 110 | 2 |  | NO | 1
4 | 20 | As a tourist, I would like to receive a reminder email the day before, so I don´t forget my trip. | 110 | 2 |  | NO | 1
4 | 7 | As a webmaster, I want to be able to verify reviews before they appear on the website, to make sure it isn't spam | 120 | 4 | 4 | YES | 2 | 2
4 | 5 | As a traveler, I would like to search for tours depending on their difficulty, so I can filter out tours I am not fit enough for | 130 | 1 | 1 | YES | 0.5 | 0.5
5 | 13 | As a tourist, I want to be able to submit a rating and a review for the guide that was on the tour I've been on, to let others know my experience and what to expect. | 140 | 3 |  | NO | 1.5
5 | 14 | As a website visitor, I want to be able to see which guide is on each tour, to check his reviews and know what to expect. | 140 | 3 |  | NO | 1.5
(á eftir að margfalda *2 til að fá klukkutíma (Í Estimated Team Effort))
|  |  |  | Est. Team effort sum | Actual Team effort sum
|  |  |  | 66 | 28
|  |  |  | Est. Team effort left [Hours] | Remaining [Hours] | Actual Effort
|  |  |  | 0 | 20 | 0
|  |  |  | 3 | 19 | 2.5
|  |  |  | 4.5 | 18 | 3
|  |  |  | 5.5 | 17 | 3.5
|  |  |  | 6 | 16 | 4
|  |  |  | 11 | 15 | 6.5
|  |  |  | 12.5 | 14 | 7.5
|  |  |  | 19 | 13 | 7.5
|  |  |  | 19.5 | 12 | 8
|  |  |  | 20 | 11 | 8.5
|  |  |  | 20.5 | 10 | 9
|  |  |  | 21.5 | 9 | 9.5
|  |  |  | 22.5 | 8 | 10
|  |  |  | 25 | 7 | 11
|  |  |  | 25.5 | 6 | 11.5
|  |  |  | 26.5 | 5 | 11.5
|  |  |  | 27.5 | 4 | 11.5
|  |  |  | 29.5 | 3 | 13.5
|  |  |  | 30 | 2 | 14
|  |  |  | 31.5 | 1 | 14
|  |  |  | 33 | 0 | 14